## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 4 | 4
Project Circuit Schematic | Abdelrhman | Done | 1 | 1.5
Drivers' Documentation | All Team | Done | 2 | 1
Low Level Design
Functions' Flowchart | All Team | Done | 3 | 4
Summary
Document File | Abdelrhman | Done | 3 | 3
Implementation
MCAL Module
DIO Driver | Mohamed | Done | 8 | 9
EXI Driver | Abdelrhman | Done | 3 | 2
TMR Driver | Hazem | Done | 3 | 6
HAL Module
BTN Driver | Mohamed | Done | 2 | 1
LCD Driver | Mohamed | Done | 8 | 7
KPD Driver | Abdelrhman | Done | 2 | 1
DCM Driver | Abdelrhman | Done | 2 | 4
ICU Driver | Hazem | Done | 3 | 2
US Driver | Hazem | Done | 2 | 1
APP Module
APP Module | Mohamed | Done | 12 | 16
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 4 | 6
Unit Testing
Test MCAL | All Team | Done | 3 | 4
Test HAL | All Team | Done | 3 | 6
System Testing
Test APP | All Team | Done | 2 | 8
Final Requirements Review | All Team | Done | 1 | 1
Video
Video Recording | All Team | Done | 1 | 1
Video Editing |  | Done | 1 | 1