## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Implementation
Implementation using Thesis (tasks.c)
Implement EDF Scheduler (Four Modifications) | Abdelrhman | Done | 3 | 2
Implement EDF Scheduler (Three Modifications) | Amr | Done | 3 | 2
Implementation of the missing changes from Thesis (tasks.c)
API: prvIdleTask | Abdelrhman | Done | 2 | 4
API: xTaskIncrementTick (Calculate the New Task Deadline) | Mohamed | Done | 2 | 1
API: xTaskIncrementTick (Modify Preemption Method) | Hazem | Done | 2 | 1
Implementation (main.c)
Tasks | Amr | Done | 3 | 3
Testing
Verification of System Implementation
Analytical Methods | Hazem | Done | 2 | 1
Keil Simulator (GPIO Pins and Logic Analyzer) | Hazem - Mohamed | Done | 6 | 7
Simso Offline Simulator | Mohamed | Done | 3 | 4
Keil Simulator (Trace Macros and Logic Analyzer) | Amr - Abdelrhman | Done | 6 | 8
Documentation
Report
Analytical Methods | Hazem | Done | 2 | 1
Keil Simulator (GPIO Pins and Logic Analyzer) | Hazem - Mohamed | Done | 3 | 4
Simso Offline Simulator | Mohamed | Done | 3 | 4
Keil Simulator (Trace Macros and Logic Analyzer) | Amr - Abdelrhman | Done | 3 | 2
Video
Video Recording | All Team | Done | 3 | 2
Video Editing | Abdelrhman | Done | 1 | 1