## Team Backlog
Team Backlog |  |  |  |  | Hacker Kermit
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 4 | 4
Project Circuit Schematic | Hossam | Done | 1 | 2
Drivers' Documentation | All Team | Done | 2 | 1
Low Level Design
Functions' Flowchart | All Team | Done | 3 | 4
Summary
Document File | Abdelrhman | Done | 3 | 3
Implementation
MCAL Module
DIO Driver | Hossam | Done | 1 | 1
EXI Driver | Abdelrhman | Done | 3 | 2
TMR Driver | Mahmoud | Done | 1 | 2
I2C Driver | Mahmoud | Done | 4 | 9
SPI Driver | Hossam | Done | 4 | 6
UART Driver | Abdelrhman | Done | 4 | 5
HAL Module
MBTN Driver (Multifunctional button) | Hossam | Done | 2 | 1
BUZ Driver | Abdelrhman | Done | 1 | 1
LCD Driver | Hossam | Done | 1 | 1
KPD Driver | Abdelrhman | Done | 3 | 2
EEPROM Driver | Mahmoud | Done | 3 | 7
APP Module
ATM ECU APP | Hossam | Done | 10 | 7
Card ECU APP | Abdelrhman | Done | 4 | 6
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 4 | 6
Unit Testing
Test MCAL | All Team | Done | 3 | 4
Test HAL | All Team | Done | 3 | 6
System Testing
Test APP | All Team | Done | 2 | 3
Final Requirements Review | All Team | Done | 1 | 1
Video
Video Recording | All Team | Done | 1 | 1
Video Editing | Hossam | Done | 1 | 1