## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 4 | 1
Drivers' Documentation | All Team | Done | 2 | 1
Low Level Design
Functions' Flowchart | All Team | Done | 6 | 8
Summary
Hardware Assembly and Debugging | Mohamed | Done | 5 | 12
Document File | All Team | Done | 3 | 6
Implementation
MCAL Module
GPIO Driver | Hazem | Done | 2 | 2
GPT Driver | Hazem | Done | 4 | 6
HAL Module
LED Driver | Hazem | Done | 2 | 1
BUTTON Driver | Hazem | Done | 2 | 1
PWM Driver | Hazem | Done | 3 | 3
DCM Driver | Abdelrhman | Done | 3 | 2
DELAY Driver | Hazem | Done | 1 | 1
EXTI Driver | Hazem | Done | 2 | 2
APP Module
APP Module | Abdelrhman | Done | 4 | 6
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 2 | 1
Unit Testing
Test MCAL | All Team | Done | 3 | 4
Test HAL | All Team | Done | 3 | 6
System Testing
Test APP | All Team | Done | 2 | 6
Final Requirements Review | All Team | Done | 1 | 1
Video
Video Recording | All Team | Done | 1 | 1
Video Editing | Abdelrhman | Done | 1 | 1